## Sheet1
Project Proposal
Cleveland State University
| Project Start: |  | 2023-03-22
[5 empty] | Week 1 |  | Week 2 | Week 3 | Week4 | Week 5
TASK | ASSIGNED TO | PROGRESS | START | END |  | Mar 22-28 | Mar 29-Apr 4 | Apr 5-11 | Apr 12-18 | Apr 19-25
Planning and Research |  |  | 2023-03-22 | 2023-03-28
Team task |  | 100%
Design |  |  | 2023-03-29 | 2023-04-05
Fabio Hinojosa Jimenez |  | 70%
Nadia Cannon
Shakeeb Rahman
Lukas Miciunas
Programming |  |  | 2023-04-02 | 2023-04-15
Angelo Figueroa |  | 20%%
Lukas Miciunas
Art Assets |  |  | 2023-04-05 | 2023-04-20
Shakeeb Rahman |  | 10%
Test |  |  | 2023-04-19 | 2023-04-26
Team task |  | 0%
Deployement |  |  | 2023-04-27 | 2023-05-01
Team task |  | 0%